## Start Here
PRINCE2 COMMUNICATION PLANNER
Plan the right information, for the right people, at the right time.
An editable working resource for project communication, reporting, feedback, and reviews. Designed to support practical application of PRINCE2 7 concepts.
GET STARTED
01 Communication Register | Identify stakeholders, information needs, communication purpose, ownership, channels, timing, and feedback routes.
02 Reporting Schedule | Agree formal reports, recipients, triggers, review arrangements, and any required action.
03 Feedback & Actions | Record stakeholder concerns, follow-up actions, owners, dates, and outcomes.
04 Review Log | Keep arrangements aligned with evolving stakeholders, project stages, and ways of working.
05 Worked Example | See how fictional customer-service platform entries could be recorded. Replace with your own project information.
HOW TO USE THIS PLANNER
• Start with the relevant audiences, including people outside the formal project team.
• Select formats and frequencies that match the purpose and audience. Do not assume everyone needs every report.
• Use agreed PRINCE2 reporting and exception arrangements. A spreadsheet does not replace formal authority.
• Include two-way feedback, not only outgoing updates. Revisit the register when relationships or project circumstances change.
IMPORTANT NOTE
Original ITonlinelearning learning resource. Not an official PeopleCert/PRINCE2 template. The official PRINCE2 7 management product is the Communication Management Approach, which forms part of the Project Initiation Documentation. This planner is a practical supplementary tool; tailor it to your project and the approved management approaches.

## Communication Register
COMMUNICATION REGISTER
Record what people need, why they need it, how they will receive it, and how they can respond.
BLUE TEXT = EDITABLE INPUT ¦ Pale teal rows are ready to complete ¦ Filter the headings to find records quickly
Audience / stakeholder | Information needed | Purpose | Owner / sender | Channel / format | Frequency / trigger | Response needed? | Feedback / response route | Access / confidentiality | Last reviewed | Next review | Notes / linked record

## Reporting Schedule
REPORTING SCHEDULE
Use the reporting arrangements agreed for your project; example reporting relationships follow PRINCE2 7.
BLUE TEXT = EDITABLE INPUT ¦ Pale teal rows are ready to complete ¦ Filter the headings to find records quickly
Report / communication | Typical sender | Recipient / audience | Purpose / decision supported | Frequency / trigger | Agreed due date | Owner | Format / location | Response / decision required | Status | Escalation / route | Notes

## Feedback & Actions
FEEDBACK & ACTIONS
Track input and decisions. A stakeholder request does not, by itself, authorise a project change.
BLUE TEXT = EDITABLE INPUT ¦ Pale teal rows are ready to complete ¦ Filter the headings to find records quickly
Reference | Date received | Stakeholder / source | Feedback or concern | Related product / area | Response / next action | Action owner | Due date | Status | Decision route / authority | Outcome / response shared | Closed date

## Review Log
COMMUNICATION REVIEW LOG
Review at relevant points, including stage boundaries and changes to important relationships or stakeholder needs.
BLUE TEXT = EDITABLE INPUT ¦ Pale teal rows are ready to complete ¦ Filter the headings to find records quickly
Review date | Trigger / reason | Stakeholders affected | What changed? | Impact on communication | Decision / agreed adjustment | Owner | Effective date | Next review date | Reference / notes

## Worked Example
WORKED EXAMPLE
Fictional customer-service platform project. Illustrations only, not compulsory PRINCE2 formats or reporting frequencies.
ILLUSTRATIVE COMMUNICATION REGISTER ENTRIES
Audience | Information needed | Purpose | Owner | Channel | Frequency / trigger | Feedback route
Project Board | Stage progress, forecasts, key risks | Oversight | Project Manager | Highlight Report | As agreed for the stage | Board questions and decisions to Project Manager
Project Manager | Work Package progress and concerns | Progress update | Team Manager | Checkpoint Report | As agreed in Work Package | Discussion and corrective-action route
End users | Usability concerns and readiness needs | Feedback | Assigned engagement owner | Demonstration / workshop | At selected review points | Capture concerns for appropriate assessment
External supplier | Requirements and dependencies | Coordination | Assigned workstream owner | Working discussion | When dependencies require attention | Confirm owner and action after discussion
Project Board | Forecast Stage Plan tolerance breach | Escalation | Project Manager | Exception Report | When a relevant exception is forecast | Decision / direction communicated to Project Manager
REPORTING REMINDERS
• Checkpoint Report: typically Team Manager → Project Manager, at Work Package-agreed intervals.
• Highlight Report: Project Manager → Project Board, at agreed reporting intervals.
• End Stage Report: Project Manager → Project Board at the end of a management stage.
• Exception Report: Project Manager → Project Board when project/stage tolerance is forecast to be exceeded.
• Not all stakeholder communication should be a formal report; provide useful listening and feedback routes.
This sheet contains fictional examples only; the editable registers are intentionally blank.