## Start Here
PRINCE2® STAKEHOLDER ENGAGEMENT PLANNER
01 What this workbook is for
Use this editable resource to identify relevant stakeholders, understand interests and impacts, plan appropriate communication, assign relationship responsibilities, and review engagement as your project progresses.
02 Complete the Stakeholder Planner
Record each stakeholder or group on a separate row. Consider people who can influence the project, are affected by it, or believe they are affected. Use qualitative ratings as discussion prompts, not automatic decisions.
03 Build your Communication Schedule
Agree what needs to be communicated, why, with whom, by which method, and when. Include opportunities to listen and receive feedback, not just broadcast information.
04 Review and respond
Use Engagement Review to capture concerns, feedback, follow-up actions, owners, and review dates. Reassess key relationships whenever circumstances change and at suitable stage boundaries.
05 See the Worked Example
A fictional HR self-service platform illustrates how the columns can be used. This is a learning example, not a prescribed PRINCE2 stakeholder model.
IMPORTANT ¦ PRINCE2 7 terminology
The official PRINCE2 7 communication management approach includes stakeholder analysis and two-way communication. This workbook is an optional supporting aid and does not replace the project’s approved management approaches.
Original ITonlinelearning learning resource. Not an official PeopleCert or PRINCE2 template. PRINCE2® is a registered trademark of PeopleCert.

## Stakeholder Planner
STAKEHOLDER PLANNER
Record people, groups, or organisations who can influence or be affected by the project.
BLUE TEXT = EDITABLE INPUT • Use the dropdowns where available • Filter columns to find information quickly
Stakeholder / group | Business / user / supplier interest | Relationship to project | How project affects them | Influence | Impact | Current support | Key interests / concerns | Required involvement | Relationship owner | Engagement priority / considerations | Last reviewed | Next review

## Communication Schedule
COMMUNICATION SCHEDULE
Plan two-way communication, consultation, and engagement with stakeholders.
BLUE TEXT = EDITABLE INPUT • Use the dropdowns where available • Filter columns to find information quickly
Stakeholder / group | Communication / engagement activity | Purpose or desired outcome | Key message / question | Channel / format | Frequency / trigger | Next planned date | Activity owner | Feedback route | Status | Notes / follow-up

## Engagement Review
ENGAGEMENT REVIEW
Record feedback, keep relationships under review, and track agreed actions.
BLUE TEXT = EDITABLE INPUT • Use the dropdowns where available • Filter columns to find information quickly
Stakeholder / group | Review date | Feedback / concern / observation | Does it require further assessment? | Related risk / issue / change reference | Agreed response or action | Action owner | Due date | Action status | Next engagement / review | Closed date

## Worked Example
WORKED EXAMPLE ¦ HR SELF-SERVICE PLATFORM
FICTIONAL EXAMPLE ONLY — copy useful ideas into the blank planning tabs and adapt to your project.
BLUE TEXT = EDITABLE INPUT • Use the dropdowns where available • Filter columns to find information quickly
Stakeholder / group | PRINCE2 interest | Project impact / concern | Suggested involvement | Suggested engagement | Possible relationship owner | Review trigger
Employees | User | Usability, privacy, and learning a new process | User / adopter | User testing, feedback sessions, clear launch support | Senior User representative | After pilot testing
Line managers | User | Changes to approvals and workload | Consulted | Workshops to understand processes and concerns | HR change lead | Before revised workflow approval
HR leadership | Business / user | Benefits, operating model, and adoption | Decision-maker | Decision-focused briefings and requirements reviews | Executive / Senior User | At stage boundary
Information security | Supplier / other | Security controls and data protection | Contributor | Early specialist input, reviews, and approvals where authorised | Technical lead | Before relevant design approval
Software supplier | Supplier | Clear requirements, dependencies, and delivery decisions | Contributor | Delivery coordination, interface reviews, issue escalation | Senior Supplier representative | When dependencies change
Payroll team | User | Accurate information flows and procedures | Consulted | Process mapping and integration testing | User representative | Before testing sign-off
Support desk | User / supplier | Readiness for post-launch user support | Contributor | Training, knowledge transfer, and support-process preparation | Operations lead | Before go-live
Illustrative guidance only. The communication management approach and change management approach should be defined and tailored for the actual project. This worked example is not official PRINCE2 guidance.